## 23 june 2016
Sl.no. | Name of 11 KV feeder | Name of village | Name of DTR | Capacity KVA | LT Poles |  | AB cable length |  | DISMATLING OF MATERIALS
[5 empty] | Total to be erected (nos) | Progress/ Completed (nos) | Total to be Strung (kms) | Completed (kms) | Conductors to be dismantled (Kms) | Completed (Kms) | Poles to be dismantled (Nos) | Completed (Nos)
1 |  | KALINAMEI CHC |  | 100 | 72 | 10 | 0 |  |  |  | 6
2 |  | KALINAMEI (2) |  | 100 | 47 | 12 | 0 |  |  |  | 3
3 |  | PUNANAMEI DON BOSCO SCHOOL |  | 100 | 48 |  | 0 |  |  |  | 3
4 |  | PUNANAMEI VILLAGE |  | 2X100 | 76 | 45 | 2.7 |  |  |  | 5
5 |  | PUDUNAMEI LOWER |  | 100 | 50 | 29 | 1.7 |  |  |  | 4
6 |  | PUDUNAMEI UPPER |  | 63 | 41 | 20 | 1.6 |  |  |  | 2
7 |  | RABUNAMEI UPPER |  | 100 | 72 | 14 | 2.2 |  |  |  | 7
8 |  | RABUNAMEI LOWER |  | 100 | 46 | 6 | 1.5 |  |  |  | 5
9 |  | TADUBI BAZAAR |  | 63 | 65 |  | 2.2 |  |  |  | 6
10 |  | TADUBI VILLAGE |  | 100 | 78 |  | 2.5 |  |  |  | 6
11 |  | UPPER SHAJOUBA |  | 100 | 58 |  | 1.7 |  |  |  | 8
12 |  | MIDDLE SHAJOUBA |  | 100 | 44 |  | 1.6 |  |  |  | 5
13 |  | LOWER SHAJOUBA |  | 100 | 62 |  | 1.7 |  |  |  | 4
14 |  | SHAJOUBAL CHURCH COLONY |  | 25 | 34 |  | 1.2 |  |  |  | 3
15 |  | MARAM BAZAAR |  | 250 | 57 |  | 0
16 |  | MAO BAZAAR |  | 500 | 134 |  | 5 |  |  |  | 11
17 |  | MAO BAZAAR |  | 100 | 64 |  | 2.5 |  |  |  | 4
18 |  | PHIKOMEI MAO |  | 63 | 39 |  | 1.5 |  |  |  | 3
19 |  | KAYINU MAO |  | 25 | 27 |  | 1 |  |  |  | 3

## 18 july 2016
Work Progress report of AB Cablling at Mao under Senapati Division.
Sl.no. | Name of 11 KV feeder | Name of village | Name of DTR | Capacity KVA | LT Poles |  | AB cable length |  | DISMATLING OF MATERIALS
[5 empty] | Total to be erected (nos) | Progress/ Completed (nos) | Total to be Strung (kms) | Completed (kms) | Conductors to be dismantled (Kms) | Completed (Kms) | Poles to be dismantled (Nos) | Completed (Nos)
1 |  | KALINAMEI CHC |  | 100 | 72 | 11 | 0 | 3-Ø=0.4km,2-Ø=0.5km,1-Ø=1km |  |  | 6
2 |  | KALINAMEI (2) |  | 100 | 47 | 12 | 0 | 3-Ø=0.5km,2-Ø=0.4km,3-Ø=0.8km |  |  | 3
3 |  | PUNANAMEI DON BOSCO SCHOOL |  | 100 | 48 | 21 | 0 | 3-Ø=0.6km,2-Ø=0.5km,3-Ø=1.2km |  |  | 3
4 |  | PUNANAMEI VILLAGE |  | 2X100 | 76 | 44 | 2.7 | 3-Ø=1km,2-Ø=1km,1-Ø=2.2km |  |  | 5
5 |  | PUDUNAMEI LOWER |  | 100 | 50 | 10 | 1.7 | 3-Ø=o.4km,2-Ø=0.5km,1-Ø=1km |  |  | 4
6 |  | PUDUNAMEI UPPER |  | 63 | 41 | 0 | 1.6 | 3-Ø=0.4km,2-Ø=0.4km,1-Ø=0.6km |  |  | 2
7 |  | RABUNAMEI UPPER |  | 100 | 72 | 19 | 2.2 | 3-Ø=0.4km,2-Ø=0.5km,1-Ø=1km |  |  | 7
8 |  | RABUNAMEI LOWER |  | 100 | 46 | 6 | 1.5 | 3-Ø=0.4km,2-Ø=0.5km,1-Ø=1km |  |  | 5
9 |  | TADUBI BAZAAR |  | 63 | 65 | 23 | 2.2 | 3-Ø=0.4km,2-Ø=0.4km,1-Ø=0.6km |  |  | 6
10 |  | TADUBI VILLAGE |  | 100 | 78 | 13 | 2.5 | 3-Ø=0.4km,2-Ø=0.5km,1-Ø=1km |  |  | 6
11 |  | UPPER SHAJOUBA |  | 100 | 58 | 0 | 1.7 | 3-Ø=0.4km,2-Ø=0.5km,1-Ø=1km |  |  | 8
12 |  | MIDDLE SHAJOUBA |  | 100 | 44 | 10 | 1.6 | 3-Ø=0.4km,2-Ø=0.5km,1-Ø=1km |  |  | 5
13 |  | LOWER SHAJOUBA |  | 100 | 62 | 14 | 1.7 | 3-Ø=0.4km,2-Ø=0.5km,1-Ø=1km |  |  | 4
14 |  | SHAJOUBAL CHURCH COLONY |  | 25 | 34 | 0 | 1.2 | 3-Ø=0.4km,2-Ø=0.4km,1-Ø=0.6km |  |  | 3
15 |  | MARAM BAZAAR (Rai Basti) |  | 250 | 57 | 60 | 0 | 3-Ø=0.8km,2-Ø=0.8km,1-Ø=2.0km
16 |  | MAO BAZAAR |  | 500 | 134 | 27 | 5 | 3-Ø=2.0km,2-Ø=2.5km,1-Ø=3.0km |  |  | 11
17 |  | MAO BAZAAR |  | 100 | 64 | 12 | 2.5 | 3-Ø=0.4km,2-Ø=0.5km,1-Ø=1km |  |  | 4
18 |  | PHIKOMEI MAO |  | 63 | 39 | 0 | 1.5 |  |  |  | 3
19 |  | KAYINU MAO |  | 25 | 27 | 0 | 1 |  |  |  | 3